## Sheet1
Portion of Project | Task | Est. Minutes | Remaining | Sprint 1 | Date | Planned | Actual
App Branding | App name | 10 |  |  | 2021-11-01 | 15 | 15
| App slogan | 5 |  |  | 2021-11-02 | 11 | 12
| App color scheme | 30 |  |  | 2021-11-03 | 9 | 11
| App fonts | 15 |  |  | 2021-11-04 | 6
| App Logo | 10 |  |  | 2021-11-05 | 5
| General App style | 2 |  |  | 2021-11-06 | 3
| High level app data display strategy | 20 |  |  | 2021-11-07 | 0
Total: |  | 92 | 0
Team Strategy | Assign project manager | 5 |  | Sprint 1 covers App Branding, Team Strategy, API usage, Home Page, and Search Page
| Assign front end developers | 5 |  | Total: | 887 | 670 | 217
| Assign back end developers | 5 |  | Total (Hours): | 14.7833 | 11.1667 | 3.6167
Total: |  | 15 | 0
API usage | Data usage from weather api | 15
| Data usage from time zone api | 5 | 5
| Data usage from hotel api | 45 | 45 | Initial Total Burndown | Date | Planned
| Data usage from flight api | 30 | 30 |  | 2021-11-01 | 47
| Strategy for using weather api | 10 |  |  | 2021-11-02 | 46
| Strategy for using time | 5 | 5 |  | 2021-11-03 | 45
| Strategy for using hotel api | 20 | 20 |  | 2021-11-04 | 44
| Strategy for using flight api | 20 | 20 |  | 2021-11-05 | 42
Total: |  | 150 | 125 |  | 2021-11-06 | 41
Home Page Tasks | High level home page design | 5 |  |  | 2021-11-07 | 40
| Integrate app logo | 5 |  |  | 2021-11-08 | 39
| Integrate button to go to search page | 15 |  |  | 2021-11-09 | 38
| Integrate button to go to quiz page | 15 |  |  | 2021-11-10 | 36
| Add footer with information | 30 |  |  | 2021-11-11 | 35
| Connect home page to search page | 15 |  |  | 2021-11-12 | 34
| Connect home page to quiz page | 15 | 15 |  | 2021-11-13 | 33
Total: |  | 100 | 15 |  | 2021-11-14 | 32
Search Page | Search page feature selection (what) | 30 | 30 |  | 2021-11-15 | 30
| High level search page design (how) | 15 | 15 |  | 2021-11-16 | 29
| Connect search page to home page | 10 | 10 |  | 2021-11-17 | 28
| Connect search page to quiz page | 5 | 5 |  | 2021-11-18 | 27
| Connect search page to results page | 30 | 30 |  | 2021-11-19 | 26
| Design of navigation between searches | 15 | 15 |  | 2021-11-20 | 24
| Design of locations search | 15 | 15 |  | 2021-11-21 | 23
| Design of flights search | 15 | 15 |  | 2021-11-22 | 22
| Design of hotels search | 15 | 15 |  | 2021-11-23 | 21
| Implementation of navigation between searches | 30 | 30 |  | 2021-11-24 | 20
| Feature selection for locations search | 15 | 15 |  | 2021-11-25 | 18
| Feature selection for flights search | 15 | 15 |  | 2021-11-26 | 17
| Feature selection for hotels search | 15 | 15 |  | 2021-11-27 | 16
| Add app logo to navigation | 5 | 5 |  | 2021-11-28 | 15
| Implement navigation between searches | 60 | 60 |  | 2021-11-29 | 14
| Implement location search bar | 30 | 30 |  | 2021-11-30 | 12
| Implement flights search bar | 30 | 30 |  | 2021-12-01 | 11
| Implement hotels search bar | 30 | 30 |  | 2021-12-02 | 10
| Design of popular vacations section | 15 | 15 |  | 2021-12-03 | 9
| Decide which default vacations to display | 30 | 30 |  | 2021-12-04 | 8
| Implementation of popular vacations section | 60 | 60 |  | 2021-12-05 | 6
| Connect popular vacations with their results page | 45 | 45 |  | 2021-12-06 | 5
Total: |  | 530 | 530 |  | 2021-12-07 | 4
Search Result Page | High level results page design | 15 | 15 |  | 2021-12-08 | 3
| Connect results page to quiz page | 10 | 10 |  | 2021-12-09 | 0
| Feature selections for locations results page | 30 | 30
| Feature selections for flights results page | 30 | 30
| Feature selections for hotels results page | 3 | 3
| Criteria for sorting locations results page | 15 | 15
| Criteria for sorting flights results page | 15 | 15
| Criteria for sorting hotels results page | 15 | 15
| Criteria for filtering locations results page | 15 | 15
| Criteria for filtering flights results page | 15 | 15
| Criteria for filtering hotels results page | 15 | 15
| Decide order for locations search results | 15 | 15
| Decide order for flights search results | 15 | 15
| Decide order for hotels search results | 15 | 15
| Implement re search bar for locations results page | 30 | 30
| Implement re search bar for flights results page | 30 | 30
| Implement re search bar for hotels results page | 30 | 30
| Implement filtering for locations results page | 60 | 60
| Implement filtering for flights results page | 30 | 30
| Implement filtering for hotels results page | 30 | 30
| Implement sorting for locations results page | 60 | 60
| Implement sorting for flights results page | 30 | 30
| Implement sorting for hotels results page | 30 | 30
| Implement results of locations results page | 60 | 60
| Implement results of flights results page | 60 | 60
| Implement results of hotels results page | 60 | 60
| Connect results of locations results page with search through api | 60 | 60
| Connect results of flights results page with search through api | 60 | 60
| Connect results of hotels results page with search through api | 60 | 60
| Navigation back to search pages | 30 | 30
| Design of other recommendations algorithm | 45 | 45
| Implementation of other recommendations algorithm | 60 | 60
| Connection of other recommendations algorithm with search results | 60 | 60
Total: |  | 1108 | 1108
Quiz | High level quiz page design | 10 | 10
| Connect quiz page to home page | 10 | 10
| Connect quiz page to search page | 10 | 10
| Quiz flow design | 5 | 5
| Quiz questions selection | 30 | 30
| Quiz answers selection | 30 | 30
| Getting quiz answers from user input | 30 | 30
| Quiz recommendation algorithm design | 45 | 45
| Quiz recommendation algorithm implementation | 60 | 60
| Quiz recommendation algorithm integration with quiz results | 90 | 90
| Connect quiz page with recommendations page | 10 | 10
| Implementation of quiz questions | 20 | 20
| Implementation of quiz answers | 25 | 25
| Implementation of submit button/event | 10 | 10
Total: |  | 385 | 385
Quiz - Recommendations | High level recommendations page design | 10 | 10
| Connect to search page | 10 | 10
| Connect to quiz page | 10 | 10
| Decide what information to list for each vacation | 45 | 45
| Decide ordering of vacations based on quiz results | 45 | 45
| Implement images for each location | 60 | 60
| Connect to results page for each location | 90 | 90
Total: |  | 270 | 270
Popular Vacations | Decide what information to use for each vacation | 15 | 15
| Decide which locations to include in our vacations | 30 | 30
| Implement these vacations into code (JSON or however we will store them) | 60 | 60
| Add popular vacations to search page | 30 | 30
| Make it so which vacations are displayed is random on each page load | 30 | 30
Total: |  | 165 | 165
Total (Minutes): |  | 2815 | 2598
Total (Hours): |  | 46.9167 | 43.3
Formulas:
Date = [Date, row above]+1